## Gantt Chart
Car Sales Analytics — Project Gantt Chart
Period: 22 Apr 2026 – 02 May 2026 ¦ Author: Siphamandla ¦ Focus: Pivot Analysis & Sales Presentation
Phase | Task | Owner | Start | End | 22 Apr | 23 Apr | 24 Apr | 25 Apr | 26 Apr | 27 Apr | 28 Apr | 29 Apr | 30 Apr | 01 May | 02 May
PLANNING
PLANNING | Confirm project scope and sales questions | Siphamandla | 22 Apr | 22 Apr
PLANNING | Review final dataset and required workbook sheets | Siphamandla | 22 Apr | 23 Apr
DATA PREPARATION
DATA PREPARATION | Validate cleaned SQL output and column formats | Siphamandla | 23 Apr | 24 Apr
DATA PREPARATION | Confirm revenue, profit and margin calculations | Siphamandla | 24 Apr | 24 Apr
DATA PREPARATION | Import dataset into Excel and fix number formats | Siphamandla | 24 Apr | 25 Apr
PIVOT TABLE ANALYSIS
PIVOT TABLE ANALYSIS | Build overall summary and KPI pivot | Siphamandla | 25 Apr | 25 Apr
PIVOT TABLE ANALYSIS | Create margin tier breakdown and loss percentage | Siphamandla | 25 Apr | 26 Apr
PIVOT TABLE ANALYSIS | Analyse revenue and profit by make/model | Siphamandla | 26 Apr | 27 Apr
PIVOT TABLE ANALYSIS | Build regional performance analysis | Siphamandla | 27 Apr | 28 Apr
PIVOT TABLE ANALYSIS | Build body type, transmission and margin analysis | Siphamandla | 28 Apr | 29 Apr
PIVOT TABLE ANALYSIS | Analyse price, mileage and year-on-year trends | Siphamandla | 29 Apr | 30 Apr
VISUALISATION & INSIGHTS
VISUALISATION & INSIGHTS | Create Excel charts for revenue, profit & margin | Siphamandla | 30 Apr | 01 May
VISUALISATION & INSIGHTS | Refine body type and regional visuals | Siphamandla | 01 May | 02 May
VISUALISATION & INSIGHTS | Write key insights for Head of Sales | Siphamandla | 02 May | 02 May
FINAL REVIEW
FINAL REVIEW | Proofread work, check numbers and prepare submission | Siphamandla | 02 May | 02 May
LEGEND |  | Planning |  |  | Timeline: 22 Apr 2026 – 02 May 2026 (submission date).
|  | Data Preparation |  |  | Tasks follow the full workflow: data → pivots → charts → insights.
Pivot Table Analysis
Visualisation & Insights
Final Review